## Task List
| Project Name | Xây dựng website quản lý học sinh cho trường Tiểu học Ngọc Liệp
| Project Manager | Đào Việt Anh
| Date | 30/09/2024
| Version | 1
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Task No. | Task Description | Task Owner | Dependency | Resources Needed | Task Status | Cost | Start Date | Estimated Completion | Finish Date | Notes
1 | Phân tích yêu cầu và thiết kế
1.1 | Khảo sát và thu thập yêu cầu
1.1.1 | Phỏng vấn ban giám hiệu
1.1.2 | Tổ chức buổi họp với giáo viên
1.1.3 | Gửi bảng khảo sát cho phụ huynh
1.2 | Xác định yêu cầu chức năng
1.2.1 | Liệt kê các yêu cầu chức năng
1.2.2 | Xác định các yêu cầu phi chức năng
1.3 | Phân tích và ưu tiên yêu cầu
1.3.1 | Đánh giá mức độ quan trọng của từng yêu cầu.
1.3.2 | Phân loại yêu cầu theo nhóm ưu tiên
1.4 | Thiết kế kiến trúc hệ thống
1.4.1 | Xác định công nghệ và nền tảng phát triển
1.4.2 | Thiết kế sơ đồ kiến trúc hệ thống
1.5 | Thiết kế giao diện người dùng (UI/UX)
1.5.1 | Phác thảo wireframe cho các trang chính
1.5.2 | Tạo mẫu giao diện (mockup) cho các trang web
1.5.3 | Thiết kế trải nghiệm người dùng (UX)
1.6 | Lập tài liệu thiết kế
2 | Phát triển và lập trình
2.1 | Cài đặt công cụ phát triển
2.1.1 | Cài đặt IDE
2.1.2 | Cài đặt và cấu hình hệ thống quản lý phiên bản
2.1.3 | Thiết lập môi trường máy chủ
2.2 | Thiết kế cơ sở dữ liệu
2.3 | Xây dựng API
2.4 | Thiết kế giao diện người dùng
2.5 | Tích hợp JavaScript
2.6 | Kiểm thử chức năng
2.7 | Tối ưu hóa hiệu suất
3 | Kiểm thử và sửa lỗi
3.1 | Xác định chiến lược kiểm thử
3.2 | Kiểm thử đơn vị (Unit Testing)
3.3 | Kiểm thử tích hợp (Integration Testing)
3.4 | Kiểm thử hiệu suất (Performance Testing)
3.5 | Kiểm thử bảo mật (Security Testing)
3.6 | Thực hiện sửa lỗi
3.7 | Kiểm thử chấp nhận người dùng (UAT)
4 | Triển khai và hướng dẫn sử dụng
4.1 | Chuẩn bị môi trường triển khai
4.2 | Triển khai ứng dụng
4.3 | Tạo tài liệu hướng dẫn
4.4 | Tổ chức buổi đào tạo
4.5 | Thiết lập kênh hỗ trợ
4.6 | Theo dõi và cải tiến
5 | Bảo trì và hỗ trợ
5.1 | Xác định quy trình bảo trì
5.2 | Kiểm tra và cập nhật phần mềm
5.3 | Sao lưu dữ liệu
5.4 | Giải quyết vấn đề của người dùng
5.5 | Cung cấp tài liệu hỗ trợ
Related Free Templates
Gantt Chart Template
Project Plan Template
Project Budget Template

## WBS Tree
WBS TREE Diagram
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## How to Use WBS Template
How to Use Our WBS Template
The following is a breakdown of the terms and sections in the task list and WBS template.
Task No.: This is a numerical listing of the deliverable, which is further distinguished as you drill down deeper from task to subtask by decimal points to make sure you know exactly where in the process you are.
Task Description: This section details what the deliverable is and also goes into the task and the subtasks necessary to complete it.
Task Owner: Every deliverable, task and subtask needs an owner to make sure the work is getting done, and that person is noted in this column.
Dependency: Some tasks cannot be started until the task before them has been completed, which means it’s dependent on that task and they should be linked. This is the space where you can note task dependencies.
Resources Needed: Whatever the task needs in terms of people, equipment, materials, etc., is listed here.
Task Status: This is where you can track the status of a specific task or subtask. The dropdown menu gives you the option of marking the task as unassigned, assigned, in progress, late or complete.
Cost: Note the financial commitment needed to get the deliverable done.
Start Date: When did work on the deliverable begin? Mark it here.
Estimated Completion: The estimated amount of time allotted for the completion of the deliverable should be noted here.
Finish Date: When the deliverable is done, note the end date here.
Using the Tree Diagram
On the second sheet there is a tree chart to visualize the work breakdown structure, from the highest level at the top to the lowest level at the bottom, where the bottom is more specific and the top more general. You don’t have to add all the extra data you filled into the previous sheet, just the deliverable, task and how every many subtasks are needed to get the work done.